## Kev
Task | Time | Comment
implement spotify login system | 2
implement summoner name search bar | 1
Implement Riot API calls to return champion ID from summoner name | 0.5
Implement playlist display | 1.5
Implement Spotify integration | 2

## Perry
Task | Estimate
Implement Riot API calls to return champion ID from summoner name | 0.5
Use champion ID to fetch static playlist link | 0.5
Use champion ID to fetch champion key words/inspiration songs to generate playlists | 0.5
Return viable playlists | 0.5
Generate database with champion IDs, names, playlists, and key words | 2

## Nathan
Task | Estimated time (hrs) | Comments
Implement Database Connectors | 0.5
Implement Spotify Backend connections | 1
Implement OAuth integration | 3
Integrate OAuth with Spotify API | 1 | Will need to rewrite dummy auth keys into actual OAuth objects
Implement Riot API calls to return champion ID from summoner name | 0.5
Use champion ID to fetch static playlist link | 0.5
Use champion ID to fetch champion key words/inspiration songs to generate playlists | 0.5
Return viable playlists | 0.5
Generate database with champion IDs, names, playlists, and key words | 2
Implement playlist display | 1.5
Implement Spotify integration | 2

## Main
Task | Time | User Story #1
implement spotify login system | 2
Implement OAuth integration | 3
Integrate OAuth with Spotify API | 1
implement summoner name search bar | 1
Implement Database Connectors | 0.5
Implement Spotify Backend connections | 1